## Slide 1: Project group 10 : MINDMAP
Member :
1.Phan Xuân Tiến(leader)
2.Lê Viết Quản Trọng
3.Trịnh Thị Thu
4.Nguyễn Thị Thủy
5.Vũ Thị Trang
6.Đào Hải Long

## Slide 2: Mindmap
*Description https://github.com/tienpx/Nhom12_K57CA/wiki
Mind map project is a web application that provides a convenient environment to creare, store, share , delete and search mind maps. When you own a account, you can :
Creare new mind maps. (Do it yourself or invite your friend to join with you.)
Store mind maps on local device as well as web account.
Share mind maps to social networking site (like facebook, Twitter..).
Search mind maps which have contents you wish in our website where other users store there mind maps and let them public.
*Platform : Ruby On Rails , Css, javascript

## Slide 3: Mindmap
Duration : 12 weeks , 10 sprints coressponding , each one last 4 weeks.

## Slide 4: Mindmap
2 first sprints : learning Ruby On Rails , js , css…
Status : done
Goals : learning Ruby on Rails, several framwork such as Css, Html , Javascript , Bootstrap
Responsibility for : all members
Result :
  Done Completely
  Member’s enthusiasm : good , all members learned in 2 weeks as planning
  Problems :
    Short time for learing
    All members are newbie , so our skill are not well-trained

## Slide 5: Mindmap
Sprint 3th : Welcome page’s interface
Begin : week 3th
Status : done ( in week 5th)
Goals :
  create welcome page,that user can see the apps name
  Create links for signing in, signing up
  Be able to show several tools that support about apps, such as wiki, help,
Responsibility for :
  Page interface : Phan Xuan Tien
  Sign in, Sign up : Nguyen Thi Thuy
Result :
  Done completely
  Problems :
    Smell code
    Not following with Agile
    Not good interface : image , layout.
Member’s enthusiasm : good

## Slide 6: Mindmap
Sprint 4th : Create a new Mindmap
Begin : 5th week
Status : done in week 9th
Goals :
  Be able to creat a new mindmap online
  Create links from welcomepage to create mindmap
  Create tools for drawing a new mindmap
  Datebase saves mindmap information
Responsibility for :
  Create mindmap : Phan Xuan Tien , Vu Thi Trang
  Create links : Vu Thi Trang
  Create tools : Trinh Thi Thu , Le Viet Quan Trong
  Database : Le Viet Quan Trong
Result :
  Essentially complete , applying Agile method
  Problems : conflix code , difficuly deals with relative features
Member’s enthusiasm : good

## Slide 7: Mindmap
Sprint 5th : Save minndmap on database
Begin : 6th week
Status : doing
Goals :
  Be able to save data on database, so that the query operation will be fast
Responsibility for : Le Viet Quan Trong
Result :
  Several steps completed
  Problems : Ruby support SQLite , so SQL server , MySql will not be easy to use , test driven problems
Member’s enthusiasm : good

## Slide 8: Mindmap
Sprint 6th : Adding, Editing , Deleting Mindmap
Begin : 7th week
Status : doing
Goals :
  Adding a new mindmap
  Editing mindmap, including name , description
  Delete unused mindmap
  Remove mindmap data from database
Responsibility for : Vu Thi Trang
Result :
  Several steps completed
  Problems : smell code ,conflix code with several members , because of relative features,
Member’s enthusiasm : good

## Slide 9: Mindmap

## Slide 10: Mindmap
Sprint 7th : Adding, Editing , Deleting User Account
Begin : 8th week
Status : done
Goals :
  User be able to create a new account
  Editing account , including name, email..in profile
  Deleting unused account
Responsibility for : Nguyen Thi Thuy
Result :
  Essentially complete
  Problems : smell code , testing , stick user with mindmap
Member’s enthusiasm : good

## Slide 11: Mindmap
Sprint 8th : Create Tools, decorate the drawing page interface
Begin : 9th week
Status : done
Goals :
  Implement some tools support for user when drawing page , such as easer , image..
  Decorate page interface
Responsibility for : Trinh Thi Thu
Result :
  Several steps completed
  Problems :
    not easy for testing html, css, boostrap
    Implement may be difficult
Member’s enthusiasm : good

## Slide 12: Mindmap
Sprint 9th : Adding feature for users
Begin : 10th week
Status : doing
  Goals :
    This apps be able to login with social network account such as facebook, gmail..
  This apps can get user information from the other account
Responsibility for : Dao Hai Long
Result :
  Several steps completed
  Problems : several problems about interface, links
Member’s enthusiasm : good

## Slide 13: Mindmap
Sprint 10th : Complete mindmap features
Begin : week 12th
Status : doing
  Goals :
    Complete several features for mindmap such as share mindmap on social network
Responsibility for : all members
Result :
  Complete testing , refactor code
  Problems : fixing conflix conflic beacause of relative features
Member’s enthusiasm : good

## Slide 14: Mindmap